## Overview
| DATE Test Load DATA WAS EXTRACTED: |  | Last update: January 2023
DATE Cutover DATA WAS EXTRACTED:
All examples must be created or loaned prior to the above date.
Sample Data Review Checklist of Alma Institution on Production |  |  | TL = Test Load CO = Cutover
This document is designed to help you gather examples from your current ILS to review *in Alma* after migration. This will help you to:
1) Understand the migration process.
2) Verify that your data migrated as specified in documentation and per your field mapping and/or migration form choices. |  | Ask your ExL project team for a custom version of this checklist!
3) Gather a ready slate of examples to check again at Cutover. |  | We are happy to hide or delete the data checks that don't apply to you migration.
** We encourage you to go beyond these guidelines if your migration included special requests, or if some aspect of your data has particular significance for you, and warrants extra review. **
Review timing:
Test Load - approximately 2 weeks for focused data review. Any major migration issues should be identified during this time. Additional issues will be found during functional/workflow review and configuration. You may continue to report such issues as found but they may not be resolved at cutover.
Cutover Load - < 2 days to verify the migration process and the integrity of the configuration. The configuration form is not uploaded again.
Reminder: Anyone performing testing should be training on Alma Essentials searching, overview and their area of expertise (Acq, Fulfillment, Resource Mgmt, etc.)
How to use this Spreadsheet
Instructions for the "Record Counts" Tab
The purpose of this tab is to help you verify how many of each record type migrated to Alma. The key is to compare the number of records in each of your data extracts^--e.g. bibs, users, invoices, etc.-- to the total number of each you see in Alma after migration.
^Note: Especially at Test Load, many weeks might pass between the time extracts are pulled from your ILS and loaded to Alma.
Alma results must be compared to your extracts, rather than to current totals in your ILS, where you likely have added inventory and users, processed further loans, etc. after extracts were pulled.
Column A: Record types you may be migrating to Alma, i.e. you are providing a extract from your current ILS to Ex Libris to migrate to Alma.
Column B: how to find the total records of each type in Alma.
Column C: Additional context for the search/comparison.
Column D: record the total records in your Test Load data extract.
Column E: record the number of rejects reported on your Test Load Migration Statistics report. (If individual records don’t meet requirements in documentation, they may not migrate to Alma.)
Column F: record the total loaded to Alma, as reported in Test Load Migration Statistics.
Column G: the total for the record type in Alma. (Does it match the number reported on Migration Statistics?)
Column H: record whether the search "Meets Expectation" in Alma for Test Load migration, or if you need to "Ask ExL" about the result you see.
Column I: record notes you want to remember for Cutover.
Column J: record the total records in your Cutover data extract.
Column K: records the number of rejects reported on your Cutover Migration Statistics report.
Column L: record the total loaded to Alma, as reported in Cutover Migration Statistics.
Column M: the total for the record type in Alma at Cutover.
Column N: record whether the search "Meets Expectation" in Alma for Cutover migration, or if you need to "Ask ExL" about the result you see.
Column O: use for notes or comments about your Cutover data migration.
Instructions for All Other Tabs
Column A : a scenario that may exist in your current ILS, whose migration outcome you should review in Alma.
Column B : metadata you should record for your example for Column A, so that you can find it in Alma after migration.
Column C : record your metadata for the scenario.
Column D : illustrates how to find your example in Alma.
Column E : more info/context on migration or what to look for in Alma.
Column F: record whether the scenario "Meets Expectation" in Alma for Test Load migration, or if you need to "Ask ExL" about the result you see.
Column G: record notes for Cutover, e.g. changes you might want to make to migration or field mapping forms for this scenario, changes to your data extract, etc.
Column H: record whether the scenario "Meets Expectation" in Alma for Cutover migration, or if you need to "Ask ExL" about the result you see.
Column I: use for notes or comments about your Cutover data migration.

## Internal Data Checks (hidden)
Topic | Description | Alma path | Status | Comments | Check against
Scope | Verify Migration scope in Migration SF case | Ex menu> All In-One Verify that all relevant loaders were executed
Libraries and Locations | Verify that the library codes in the configuration form are exactly the same as those that were migrated. | General Configuration Menu> Libraries> Add a Library or Edit Library Information> Libraries Tab |  |  | For Aleph: config. form, for other ILS: migration form
| Verify that the location codes in the configuration form are the same as those that were migrated | Fulfillment Configuration Menu> Choose and check the locations per library from the dropdown list |  |  | For Aleph: config. form, for other ILS: migration form
Bibs | Make sure libraries and locations migrated properly, by checking whether items in Alma are available – see availability field with a link to physical or electronic items | Search for a general subject in "All Titles", i.e. history, math or the article "the" in order to receive multiple results. If these results aren’t satisfying or cause concern, try searching for ‘*’ to see all records.
| Check if there are Orders with Linked Records. | Check "More Info" of several items. You can also search first for Order Lines and then search for the attached Bib in the general search.
| Check if there are CZ packages and portfolios: means that Link Resolver migration was run | Search for '*' in electronic portfolios, look for CZ results.
| Check if there are local packages and portfolios: means that physical and electronic processes have been run | Search for '*' in electronic portfolios, look for local results. |  |  | P2E was run
Items | Check the distribution of items. | Search for a general subject in "Physical Items", i.e. history, math, the article "the" , or wildcard '*', Looking through the facets:
Libraries – if there are several, make sure there are items in each library
Item Material Type – most of the items should be classified. Electronic items may not be classified and will have then a call number "problem". The customer should be informed, if there are more than single thousands of this type
Process Type – the number of items here is usually less than the total number of the items, since not all the items have processes. There is a type "Technical Migration" that includes not available items (items that are not on loan and not on shelf), and the reason is noted in the items themselves. Red flag – there is no "Technical Migration" type
Check if there are items that are "not in place". Red flag – there are more than single thousand of them
Check if there are items in UNASSIGNED location. Red flag – there are more than single thousand of them
| Holding record should have call number, library and location | Click the "Holdings" links in the search results.
Users - Loans | Pick from the facets the process type "Loan" to see all the loaned items | Search for a general subject in "Physical Items", i.e. history, math , the article "the" , or wildcard '*'.
Click on the "Loan" link of several items to make sure the info is logically built – loan status, due date, etc.
| Check if the loaning users indeed have the loans on the items | Search for specific users in the users persistent search and click "fulfillment activities"
Users - Details and Identifiers | While in the specific user account, check if there are notes, address, phone number, e-mail, and identifiers (e.g. barcode). Make sure the details look logical. | The identifiers are configured under General > All Code Tables> User Identifier Type. They should be identical to the identifiers that appear in the user account, but not all users will have all identifiers. Red flag while checking users: Identifier that don't appear on the code table or missing e-mail address
Users - Requests | If there are requests, check some of them the same way you did in loans above. | In order to access the Requests, you must first add an operator role for the OTB Circ desk. to the exl users via Fulfilment > Configuration Menu > Circulation Desks > Edit Circ desk > Operator Tab > Add operator. Search for "the" from the persistent menu "Requests". If you can’t find any requests in the search, check the “monitor requests” page to see if there are any.
Acquisitions - Funds To verify If there was an acquisitions migration check Administration > All-in-One | Make sure there’s an active funds for the current active fiscal period. | Acquisition configuration menu > Fund and Ledger Fiscal Period
| Check if the fiscal period is correct. Red flag: There's only one fiscal period. |  |  |  | Migration form
| Make sure there are allocated funds | Go to Acquisitions Infrastructure > Funds and Ledgers. If you don't see any funds, remove the "Active' filter.
| Check its facets: the ledger should contain several libraries | Pick a ledger from the facets
The Cash Balance of a fund should be positive.The Encumbered Balance may be negative
| Vendors and Vendor Accounts | Acquisitions Infrastructure > Vendors
Acquisitions - PO Lines | Look through the facets and make sure the orders divided logically between vendors, libraries etc. | Search for "the" from the persistent menu "Order Lines"
There should be more than one Purchase Type
Open orders should have funds - Orders with acquisition method Depository, Gift or Technical do not attain fund associations by Alma design.
| Check there are funds in orders and it is 100% | Pick from the facets a "Waiting for Renewal" status and pick for Acquisition Method either "Purchase" or "Purchase at Vendor System" (whichever has more)
Vendor/Accounts field is filled
Copies field is filled (in the brief search results page). Physical subscription orders should have copies. If this is a standing or one-time order there may be no copies
For Item Material Type "Book" the order type should be "Print Book – One time (unless the customer mapped it to physical one time in their migration form)
Some purchase orders have notes
| Check for Electronic PO Lines, and their association with Electronic inventory records |  |  |  | P2E was run
| Receiving: make sure the One Time Orders are really one time and Subscriptions are subscriptions | Check the Receiving Workbench (Acquisitions > Receiving and Invoicing> Receive) In order to access the Receiving page, you must first add an operator role for the OTB acquisitions dept. to the exl users via Administration > configuration Menu > Work Order Departments > Edit Acquisitions Department > Operator Tab > Add operator
Acquisitions - Invoices | Make sure the invoices are logically divided by vendors | To retrieve large amount of invoices - search for '1*'
| Check the status: most of the invoices should be closed | To retrieve large amount of invoices - search for '1*' (total number of invoices cannot be counted using the UI as search doesn't support it) |  |  | Tips for this check: 1) Look in the counter of the loader 2) Use the task list for "In-Reivew" invoices
| The fields "Price" and "Fund" should be filled | Click "Edit" on two of them and check the Invoice Lines Tab
The fund should be 100%
Each line that has "Price" should have a "Fund"
PO Line field will almost always be populated for invoice lines, but in some minority cases it won't be. If no PO Line is present for many/most invoice lines, this is a red flag
If applicable, check that the invoice has other charges such as Shipment, Discount etc.
Counter Data | For Premium Migration/Cohort contract, if Counter Data was migrated, check the data was migrated | For TL- Verify that there is at least one entry in the Subscribers code table (the data will appear in Analytics only after nightly ETL). For CO and TL- check the relevant loader (see "Check against" column). |  |  | To verify check on Exlibris menu > All-in-One. Counter data from USTAT will be loaded with "Import Ustat Reports" loader. Counter data from 360 will be loaded using "Import Statistics from PQ (COUNTER)" loader.
Licenses | For ERM migration, check that liceses were loaded and that the terms are not empty | Alma mene > Acquisistions > Acquisitions Infrastructure
|  | Total Scenarios | 42
|  | Passed | 0
|  | Failed | 0
|  | N.A | 0
|  | Total Execution | 0

## Record Counts
Compare record counts in your extracts to migrated records in Alma. | How to produce count results in Alma: Menu Options or Alma Advanced Search | Additional Information | Test Load - Delivered Files List | Test Load - Rejects Reported in Stats | Test Load - ExL Migration Statistics Report | Test Load | Meets Expectation, or Ask ExL? | Note anything you want to reference at Cutover (CO) | Cutover - Delivered Files List | Cutover - ExL Migration Statistics Report | Cutover - Rejects Reported in Stats | Cutover | Meets Expectation, or Ask ExL? | AT CO, review 'Ask ExL' items first
Consult with your ExL team on which record types below apply to your migration. | Alma Path/Search | Ask your ExL consultant for more info if needed. | How many were in your data extract? | How many records in this extract were *not* migrated, for specified reasons? | How many were loaded to Alma? | # Results of Alma search (see Column B for how to find this number) | TL Status | TL Comment/Results | # from Delivered Files List | # from Migration Stats | # rejects from Migration Stats | # Results in Alma | CO Status | CO Comments/Results
Total Bib Records | Advanced Search: All titles → MMS ID > 1 | The total bib count on Migration Stats will be lower than what you see in Alma. Stats reflect bibs from your ILS and link resolver migration; doesn't include PQIS and eBook Central activations. | N/A; count is informational | N/A |  |  |  |  | N/A; count is informational | N/A
Bibs from ILS extract | Advanced Search: All titles → Originating System > Contains Keywords > "ILS" | This search reveals the number of bibs migrated to Alma only from your bib extracts (.mrc files). It will not include any link resolver migration.
Suppressed Bib Records | Advanced search: All titles → Tag Suppressed (Title) = Yes AND Originating System > Contains Keywords > ILS | This total will include any suppressed bibs from your .mrc files. Removing the "Keyword=ILS" condition will return any suppressed title (e.g. linked to the CZ) in Alma. |  | N/A; no discreet reporting for suppressed bibs. | N/A; no discreet reporting for suppressed bibs. |  |  |  |  | N/A; no discreet reporting for suppressed bibs. | N/A; no discreet reporting for suppressed bibs.
MARC Holding Records | Simple search: Physical holdings > Keywords > * | This number should match Migration Stats, but may not match total records in your MARC holdings extract. Holdings may also be created during migration. To see the number of titles with one or more physical holdings: Advanced Search > Physical titles → MMS ID > 1
Checkin Records | Physical titles → MMS ID > 1 AND Item policy = Issues | A "physical title" is any bib with at least one holding record attached (but it could have >1). Alma results will not be accurate to the number of checkin records. You will want to spot check records to confirm holdings migrated as expected.
Bibs whose physical inventory has no assigned location | Physical titles > Permanent physical location = "UNASSIGNED" location in each library | Checks for bibs whose physical inventory has no assigned location. Location in Alma depends in part on migration form location mapping. Make changes to data or location mapping for Cutover to reduce inventory in UNASSIGNED. |  | N/A; informational check | N/A; informational check |  |  |  |  | N/A; informational check | N/A; informational check
Item Records | Physical items → MMS ID > 1 | Alma total items is likely smaller than the number delivered, as some items may have been converted to e-inventory during P2E
Vendors | Acquisitions menu → Acquisitions Infrastructure → Vendors | Clear any filters to see All results, and not just active vendors
Order Records | Order lines → All → * | Returns all POLs in Alma.
Funds | Acquisitions menu → Acquisitions Infrastructure → Funds and Ledgers | Clear filters to see all funds. Depending on your fund extract, Ledgers may have been created during migration.
Invoice Records | Invoices → All → "?" | Not relevant for III migrations: data migrated to PO or POL notes
Patron Records | Admin menu → User Management → Manage Users | All migrated patrons appear on the "Public" tab
Loan Records | Physical items → Process Type = Loan AND Physical items → Process Type = Lost | Depending on ILS migration rules, some open loans may migrate with process type of "lost" or "Claimed Returned."
Fine/Fee Records | Advanced search → Users → Fine/Fee Total > 1 | Alma retrieves number of patrons with fines, while data files will be number of fines; Alma search will be lower than data provided
Request Records | Physical items → Process Type = Hold Shelf | If hold shelf total seems low, go to: Fulfillment Menu > Resource Requests > Monitor Requests & Item Processes
Courses | Fulfillment menu → Course Reserves → Courses | Depending on your extract, course total in Alma may be lower than total lines in the extract, e.g. if extract includes > 1 citation per course.
P2E Portfolios | Electronic portfolios → Is standalone = Yes AND Originating System = ILS | Note that the number in Alma is likely larger than the number on the P2E file, as a portfolio is created for every URL field (usually 856¦u) in a bib record. Your link resolver migration may also produce standlaone portfolios that will be included in the result.
P2E Databases | Electronic collections → Is linked = No AND Electronic Collection Type = Database | Count in Alma may be higher, if the title has > 1 URL. (Explained in row above.)
LR Portfolios | Electronic portfolios → Is standalone = No | Total depends on Alma packages; nothing in data to compare to directly. | N/A | [5 empty] | N/A
LR Collections | Electronic collections → Is linked = Yes | Results of the Alma search will be higher than total in Migration Stats, which does not include PQIS activations and eBook Central activations. | N/A | [5 empty] | N/A
| Test Load | Cutover
Total Scenarios | 20 | 20
Meets Expectation | 0 | 0
Ask ExL | 0 | 0
N.A | 0 | 0
Total Execution | 0 | 0

## Bibs
[5 empty] | Meets Expectation, or Ask ExL? | Note anything you want to reference at Cutover (CO) | Meets Expectation, or Ask ExL? | AT CO, review 'Ask ExL' items from TL first
Gather examples of various scenarios from your ILS to review in Alma after migration. | Prior to receiving test load, find ILS records to review. |  | How to locate results in Alma | Additional Information | TL Status | TL Comment/Results | CO Status | CO Comments/Results
Suggested Examples | Suggested Metadata |  | All searches below are possible from Alma simple search. | Results may depend on migration form, field mapping, or other migration inputs. Ask your ExL consultant for more info if needed. | Select from dropdown |  | Select from dropdown
Full bib record | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Reminder: The original ILS bib id will be added to 035 or 935, depending on migration form, otherwise records should migrate as-is. Spot check as many as you would like. Other search suggestions on this page can help with locating a variety of bibs to review.
Title:
If Acq was migrated, test the link from a bib to an Order (use a continuations/subscription title) | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Link to an active order will be visible in the Alma brief results.
Title:
Withdrawn bib which should not migrate | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | If the bib is present in Alma, you may need to reassess the criteria you used for extracting bibs from your current ILS.
Title:
Brief/circ temporary record | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C}
Title:
"On order" bib record (if migrated Acq), where inventory is not yet received | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C}
Title:
Bib records linked to a boundwith item | Unique item ID (barcode): |  | All titles → Keyword = {id or title from Column C} | Check that bibs link to host record, and host links to all related bib records.
Title/unique Bib ID for boundwith member #1:
Title/unique Bib ID for boundwith member #2:
Related records where there are analytic entries tied to a series bib or a journal title with preceding/succeeding titles (77x tags in the bib) | ISSN: |  | All titles → Keyword = {ISSN or title from Column C}
Title/ID of the record/journal with 77x tags:
Diacritics for non-English languages | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Migration of diacritics depends, in part, on correctly declaring bib encoding.
Title:
Bib with a single item | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Review holdings and items attached to the bib record by expanding the brief results. The number of holdings for this title will depend on migration form preferences.
Title:
Number of items and holdings expected:
Bib with multiple physical copies--same location | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Review holdings and items attached to the bib record; the number of holdings for this title will depend on migration from preferences.
Title:
Number of items and holdings expected:
Bib with multiple physical copies--different locations | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Review holdings and items attached to the bib record; the number of holdings for this title will depend on migration from preferences.
Title:
Number of items and holdings expected:
A monograph with multiple volumes on a single holding location | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Holdings will be determined by migration form specifications: holdings can be determined by location, or location/call no. Review holdings and items attached to the bib.
Title:
View holdings/items:
A monograph with multiple volumes and copies in multiple locations | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Review holdings and items attached to the bib record
Title:
View holdings/items:
A serial with multiple volumes on a single holding location | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Review holdings and items attached to the bib record
Title:
View holdings/items:
A serial with multiple volumes and copies in multiple locations | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Review holdings and items attached to the bib record
Title:
View holdings/items:
Bib for a right-to-left language (e.g. Hebrew) if line 11 check was for a left-to-right language | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Migration of diacritics depends, in part, on correctly declaring bib encoding.
Title:
Bib record included on P2E file | Bib id from P2E file: |  | All titles → Keyword = {id or title from Column C} | Check the number of portfolios created from the P2E is accurate (there should be at least one portfolio for each P2E URL field (usually 856¦u).
# portfolios expected for this title:
Title with physical and electronic inventory (on the same bib) | Unique Bib ID (035, LCCN, catalog key): |  | All titles → Keyword = {id or title from Column C} | Review holdings and confirm that there are both electronic and physical holdings. Note: inventory will only be migrated as electronic if correctly specified on the P2E list and migration form.
Title:
|  |  | Test Load | Cutover
|  | Total Scenarios | 18 | 18
|  | Meets Expectation | 0 | 0
|  | Ask ExL | 0 | 0
|  | N.A | 0 | 0
|  | Total Execution | 0 | 0

## Holdings
[5 empty] | Meets Expectation, or Ask ExL? | Note anything you want to reference at Cutover (CO) | Meets Expectation, or Ask ExL? | AT CO, review 'Ask ExL" items from TL first
Gather examples of various scenarios from your ILS to review in Alma after migration | Prior to receiving test load, find ILS records to review. |  | How to locate results in Alma | Additional Information | TL Status | TL Comment/Results | CO Status | CO Comments/Results
General Scenarios | Expected Counts |  | Use Alma Advanced Search | Results may depend on migration form, field mapping, or other migration inputs. Ask your ExL consultant for more info if needed. | Select from dropdown |  | Select from dropdown
Verify counts of ILS holdings in Alma libraries and locations | Sample library/location #1; est. holding count: |  | Physical titles → Permanent physical location = {individual location} | Review results for specific locations, and confirm the numbers are close (if not exact) to expectations. Alma searches should take into account the location mapping provided on the migration form.
Sample library/location #2; est. holding count:
Sample library/location #3; est. holding count:
Bibs where holding has no item records | Count of records with no physical holdings in current ILS |  | Physical titles → Has items = No | Review the list of results, and determine whether or not these records should have had physical items attached.
Specific Scenarios | Prior to receiving test load, find ILS records to review. Suggested metadata to collect. |  | Use Alma Simple Search
Bibs with multiple holding records for the same library | 035a, or other unique id (bib id, LCCN): |  | Physical titles → Keyword = {record identifier} | Review holdings and items attached to the bib record; the number of holdings for this title will depend on migration from preferences.
Title:
Expected Holding Location #1:
Call No #1:
Holding Location #2:
Call No #2:
Verify bibs with suppressed holding | 035a, or other unique id (bib id, LCCN): |  | Physical titles → Keyword = {record identifier} | Verify the holding is recorded as suppressed in Alma via the suppress icon in the results list. Holdings are suppressed via migration form preferences on the "Alma Location" tab.
Title:
Bibs with at least 2 holdings/items for different locations. | 035a, or other unique id (bib id, LCCN): |  | Physical titles > Keyword = {record identifier}
Title:
Expected holding location and call numbers:
Holdings which have notes (852z) | Unique Bib ID (035, LCCN, catalog key): |  | Physical titles → Keyword = {record identifier} | Whether holdings have notes depends on the data extracts provided and field mapping choices.
Title:
Expected notes:
Holding which includes copy information in the 852 | 035a, or other unique id: |  | Physical titles → Keyword = {record identifier}
Title:
Expected copy info:
Holding which include multi-volume set information | 035a, or other unique id: |  | Physical titles → Keyword = {record identifier}
Title:
Expected multi-volume info:
Holding for serials with summary holdings 86x tags | 035a, or other unique id (bib id, LCCN) |  | Physical titles → Keyword = {record identifier}
Title:
Expected in 86x field:
Holdings for serials with pattern information 85x/86x data | 035a, or other unique id: |  | Physical titles → Keyword = {record identifier}
Title:
Expected pattern information:
|  |  | Test Load | Cutover
|  | Total Scenarios | 10 | 10
|  | Meets Expectation | 0 | 0
|  | Ask ExL | 0 | 0
|  | N.A | 0 | 0
|  | Total Execution | 0 | 0

## Items
[5 empty] | Meets Expectation, or Ask ExL? | Note anything you want to reference at Cutover (CO) | Meets Expectation, or Ask ExL? | AT CO, review 'Ask ExL' items first
Gather examples of various scenarios from your ILS to review in Alma after migration. | Prior to receiving test load, find ILS records to review. |  | Locating Your Example in Alma | Additional Information | TL Status | TL Comment/Results | CO Status | CO Comments/Results
Description | Suggested metadata to collect. |  | How to locate results in Alma - unless using a menu option, use Advanced Search | Results may depend on migration form, field mapping, or other migration inputs. Ask your ExL consultant for more info if needed. | Select from dropdown |  | Select from dropdown
Verify item in temporary location migrated correctly | Item Barcode: |  | Physical items → barcode = {item barcode from Column C} | Alma Library and Location will be visible in the brief results.
Title:
ILS temporary library/location:
Expected Alma library/location:
Verify item locations match holding locations | Item Barcode: |  | Physical items → barcode = {item barcode from Column C} | Check item location in brief result, and holding location from the "…"/row actions menu, as pictured.
Title:
Items with notes | Item Barcode: |  | Physical items → barcode = {item barcode C} | Verify field mapping has been applied to notes, including type (e.g. public or internal).
Title:
Expected note text:
Item with a "loan" status (from loan extract provided to ExL) | Item Barcode: |  | Physical items → barcode = {item barcode from Column C}; Click "Loan" in brief result | Verify borrower and data info in the loan window.
Title:
Patron Name:
Due Date:
Item with a "lost" book status (from loan extract provided to ExL | Item Barcode: |  | Physical items → barcode = {item barcode} → click Process type: "Lost" to see patron name under 'Borrower' | Some loans will be flipped to process type "Lost" during migration. Typically it is based on the number of overdue notices sent; consult documentation for your ILS.
Title:
Patron Name/ID:
Item with a "Hold," waiting for pickup | Item Barcode: |  | Physical items > Barcode - {item barcode from Column C}; Click "Hold Shelf" in brief result | Verify requestor and date information in the hold window.
Title:
Patron Name/ID:
Hold Date:
Other Item Statuses or Process Types | "On Shelf" example Barcode: |  | Physical items > Barcode = {barcode from Column c}; Check Process type" in brief results for status If Technical Migration > Edit Item > "Notes" tab > Internal Note specified in documentation for status | Whether an item is on the shelf "in place" vs. off-shelf/"not in place" in Alma depends on Item Base status mapping for most migrations. Refer to your documentation. "Not in place" items will likely migrate with process type "Technical Migration," and an item level note that reflects the original status.
"On shelf" Title:
"Not On Shelf" example Barcode:
"Not on Shelf" title:
Bound-volume or boundwith items | Item barcode: |  | Physical items → barcode = {item barcode} | Confirm that the item's call number is accurate for all related bib records
Location Code:
Bib ID for bound title #1:
Bib ID for bound title #2:
|  |  | Test Load | Cutover
|  | Total Scenarios | 8 | 8
|  | Meets Expectation | 0 | 0
|  | Ask ExL | 0 | 0
|  | N.A | 0 | 0
|  | Total Execution | 0 | 0

## P2E
[5 empty] | Meets Expectation, or Ask ExL? | Note anything you want to reference at Cutover (CO) | Meets Expectation, or Ask ExL? | AT CO, review 'Ask ExL' items first
Gather examples of various scenarios from your ILS to review in Alma after migration | Prior to receiving test load, find ILS records to review. |  | Search Criteria or Alma path | Additional Information | TL Status | TL Comment/Results | CO Status | CO Comments/Results
General Scenarios | Expected Counts |  | How to locate results in Alma - unless using a menu option, use Advanced Search | Results may depend on migration form, field mapping, or other migration inputs. Ask your consultant for more info if needed. | Select from dropdown |  | Select from dropdown
Check P2E db collections were activated | Total count of bib ids from P2E file with type "db" (database): |  | Electronic collection → Is local = Yes | Not all implementations will have db collections in the P2E file
Check P2E portfolios were created | Total count of bib ids from P2E file with type "portfolio": |  | Electronic portfolios → Is standalone = Yes
Specific Searches | Prior to receiving test load, find ILS records to review. Suggested metadata to collect.
Check local bib that should only have electronic holding, no physical holding | bib id from P2E file with type "portfolio": |  | All titles → keyword → bib id from P2E | Must search "All titles" to see all holdings. Verify provider and public note are correct on the portfolio, and no physical item was retained in an e-location (as specified on the migration form).
Check local bib that should have both an electronic holding and a physical holding | Title from P2E: |  | All titles → Title of bib id from P2E (must search by "All Titles" to see both types of holdings) | Verify provider and public note are correct on the portfolio, and verify physical holding/item retained and e-resource was created
Bib Id:
Check that orders on P2E bibs were also changed to Electronic Types | 035a or title search then 'link': |  | Electronic Title → Title → Look for Order in top right of brief bib, click on the number. Verify order type is 'electronic' | If bib ID was included on P2E input, verify associated Acq order is an Electronic type, and order information was retained.
Order ID associated with the title:
Suppressed bib or suppressed electronic holding location for a bib id in the P2E (856 may or may not exist)** | 035a or Title for a suppressed record which would need its Order changed to Electronic (most likely a vendor package record like Ebscohost or ProQuest)** |  | Search All Titles for bib id from P2E | **ONLY RELEVANT FOR VOYAGER MIGRATIONS: Only works if Migration Form-Questionnaire Tab has answers of "YES" to final questions "include suppressed" bib/holding records with P2E. Portfolio may be created but will be null URLs. Purpose is to change Acq order to electronic.
Check standalone (P2E) portfolio is accessible on campus | Portfolio title from local bib record: |  | Advanced Search → Electronic Portfolios→ is Standalone = yes Select one of the titles OR Electronic Portfolio → Title→ from 3 ellipses to right of title, click Test Access | Testing in Alma is at the title level. Special parameters may need to be entered to test access. Testing in Primo VE can be at the article level. On campus, access should be immediate due to IP range.
Check standalone (P2E) portfolio is accessible off campus | Portfolio title from local bib record: |  | Advanced Search → Electronic Portfolios→ is Standalone = yes Select one of the titles OR Electronic Portfolio → Title→ from 3 ellipses to right of title, click Test Access | Testing in Alma is at the title level. Special parameters may need to be entered to test access. Testing in Primo VE can be at the article level. Off campus, access should prompt for proxy login unless authentication is configured.
|  |  | Test Load | Cutover
|  | Total Scenarios | 8 | 8
|  | Meets Expectation | 0 | 0
|  | Ask ExL | 0 | 0
|  | N.A | 0 | 0
|  | Total Execution | 0 | 0

## Link Resolver
[5 empty] | Meets Expectation, or Ask ExL? | Note anything you want to reference at Cutover (CO) | Meets Expectation, or Ask ExL? | AT CO, review 'Ask ExL' items first
Suggestions for types of searches to check how activations migrated to Alma | SFX/360/Link Resolver records to review |  | How to locate results with Alma Advanced Search | Additional Information | TL Status | TL Comment/Results | CO Status | CO Comments/Results
General Searches | Record expected counts |  | Alma path | Results may depend on many factors. Consult documentation for your link resolver or ask your consultant for more info if needed. | Select from dropdown |  | Select from dropdown
Check LR collections were activated | Expected number of E-Collections from Link Resolver Migration: |  | Electronic collection → Is local (Electronic collection) = No | This can be an ongoing review during the test load period, but at least compare the number of collections and spot check a few collection titles expected to be activated
Check selective package collections were properly activated | Selective Package Name, #1: |  | Electronic collection → Is local (Electronic collection) = No; Electronic Collection Type = Selective Package | This can be an ongoing review during the test load period, but at least spot check a few selective package collections and compare portfolio lists to confirm the correct individual titles were activated.
Selective Package Name, #2:
Specific Searches | Prior to receiving test load, find records to review. Suggested metadata to collect:
E-journal title from Link Resolver migration | Journal title: |  | All titles → Keyword = {id or title from example} | Expanding the brief title/bib record will reveal the portfolio details.
Journal is part of collection:
E-Collection title record from Link Resolver migration | Collection Name/Title: |  | All titles → Keyword = {id or title from example} | Migrated electronic collections will also have a suppressed bib record, separate from the collection record.
Test access to a title from a link resolver portfolio while on campus | Portfolio title from Link Resolver collection: |  | All titles → Keyword = {id or title from example}; from ellipses to right of title, click "Test Access" | Testing in Alma is at the title level. Special parameters may need to be entered to test access. Testing in Primo VE can be at the article level. On campus, access should be immediate due to IP range.
Test access to a title from a link resolver portfolio while off campus | Portfolio title from Link Resolver collection: |  | All titles → Keyword = {id or title from example}; from ellipses to right of title, click "Test Access" | Testing in Alma is at the title level. Special parameters may need to be entered to test access. Testing in Primo VE can be at the article level. Off campus, access should prompt for proxy login unless authentication is configured.
|  |  | Test Load | Cutover
|  | Total Scenarios | 6 | 6
|  | Meets Expectation | 0 | 0
|  | Ask ExL | 0 | 0
|  | N.A | 0 | 0
|  | Total Execution | 0 | 0

## Fulfillment
[5 empty] | Meets Expectation, or Ask ExL? | Note anything you want to reference at Cutover (CO) | Meets Expectation, or Ask ExL? | AT CO, review 'Ask ExL' items first
Gather examples of various scenarios from your ILS to review in Alma after migration. | Prior to receiving test load, find ILS records to review. |  | How to locate results in Alma. Unless using a menu option, use Advanced Search | Additional Information | TL Status | TL Comment/Results | CO Status | CO Comments/Results
Specific Searches | Suggested metadata to collect. |  | Alma path | Results may depend on migration form, field mapping, or other migration inputs. Ask your consultant for more info if needed. | Select from dropdown |  | Select from dropdown
Number of blocked patrons | Number of patrons with a "general" block: |  | Users > Has block type > Equals > {use dropdown} | The Alma block type depends in part on migration form mapping; also consult documentation about block migration for your ILS.
Number of patrons with other block type:
Suspended/blocked patron | Patron name and/or primary identifier: |  | Users → Primary identifier = {patron identifier} Inspect "Blocks" tab for this user
Reason for Suspension/block:
Patron with "external" patron group | Patron name / primary identifier: |  | Users → Primary identifier = {patron identifier}; Verify "Account Type" is "External" | "External" patrons are owned/updated by your HR system/SIS. User Groups are mapped and specified "internal" or "external" on the migration form.
Patron Group:
Patron with "internal" patron group | Patron name / primary identifier: |  | Users → Primary identifier = {patron identifier}: Verify account type is "internal" | "Internal" patron records will not be updated as part of the HR/SIS update process.
Patron Group:
Different patrons with the same names (and different identifiers) | Patron 1 name and primary identifier: |  | Users → Last name = {patron last name} | Verify both patrons loaded correctly, are attached to the correct identifiers, loans etc.
Patron 2 name and primary identifier:
Patron contact information | Patron name and/or primary identifier: |  | Users → Primary identifier = {patron identifier} Select Contact tab | Verify address, phone and email are mapped correctly and marked "preferred."
Phone
Email:
Address:
Patron with active fines/fees | Patron name / primary identifier: |  | Users → Primary identifier = {patron identifier} Select Fines/Fees tab | Fines/fees will be on patron record; item information will be in 'note' of fine rather than linked to item. Inactive fines/fees are not migrated.
Amount of outstanding fees:
Patron with current loans | Patron name/primary identifier: |  | Users → Primary identifier = {patron identifier}; select "Manage Fulfillment Activities" from sidebar | Inactive loans are not migrated. Items on loan may have process type "Lost" instead of loan, depending on the number of overdues. Verify loan details are correct.
Title or Barcode of Item on Loan:
Patron with lost items | Patron name / primary identifier: |  | Users → Primary identifier = {patron identifier}; select "Manage Fulfillment Activities" from sidebar | Verify loan information and any related fines/fees are correct.
Title or barcode of lost item:
Patron with statistical categories | Patron name / primary identifier: |  | Users → Primary identifier = {patron identifier}; select Statistics tab | Code table for statistical categories may not have migrated. If not, advanced search for statistical category will not work. Add code table post-test load.
Statistical Category Code and Description:
Patron with notes | Patron name / primary identifier: |  | Users → Primary identifier = {patron identifier} Select "Notes" tab | Verify notes migrated correctly. Field mapping choices determine the type of a migrated note, and whether it is internal only, or visible to the patron.
Note type and text:
Patron with item on hold shelf | Patron name / primary identifier: |  | Fulfillment menu → Resource Requests → Active Hold Shelf OR Users → Primary identifier = {patron identifier}; select "Manage Fulfillment Activities" from sidebar → Requests tab | Only holds/requests waiting for pickup are migrated. Verify requestor information migrated correctly.
Title or barcode of item on hold:
Patron record - expired patron | Patron name and primary identifier |  | Users → Primary identifier = {patron identifier} | All patrons will migrate with Alma 'active' status. Are expiration and purge dates correct?
Patron with multiple patron groups (only one will migrate) | Patron name / primary identifier: |  | Users → barcode → check record for user group | First SIS update will correct patron user group if necessary.
Patron groups in the user record:
Patron with multiple identifiers (institution id, barcodes, etc.) | Patron name: |  | Users → Primary identifier = {patron identifier}; select Identifiers tab | Verify all incoming IDs mapped to the correct Alma IDs.
Identifier #1:
Identifier #2:
Patron with multiple physical addresses | Patron name / primary identifier: |  | Users → Primary identifier = {patron identifier} Select Contact tab | All exist; one is marked Preferred
Expected address #1:
Expected address #1:
Patron with multiple phone numbers | Patron name/primary identifier: |  | Users → Primary identifier = {patron identifier}; select Contact tab | All exist; one is marked Preferred
Expected Phone number #1:
Expected Phone number #2:
Patron with multiple email addresses | Patron name / primary identifier: |  | Users → Primary identifier = {patron identifier}; select Contact tab | All exist; one is marked Preferred
Expected email #1, and type:
Expected email #2, and type:
Patron with a large number of loans | Patron Name / primary identifier: |  | Users → Primary identifier = {patron identifier}; select "Manage Fulfillment Activities" from sidebar → Loans tab | Patron fulfillment activity is also available from: Fulfillment menu → Checkout/Checkin → Manage Patron Services → {patron identifier} Set Loan Display filter to 'All Loans'
Number of loans in extract:
|  |  | Test Load | Cutover
|  | Total Scenarios | 18 | 18
|  | Meets Expectation | 0 | 0
|  | Ask ExL | 0 | 0
|  | N.A | 0 | 0
|  | Total Execution | 0 | 0

## Courses
Suggestions for types of searches to check how data migrated from your ILS to Alma |  |  |  |  | Meets Expectation, or Ask ExL? | Note anything you want to reference at Cutover (CO) | Meets Expectation, or Ask ExL? | AT CO, review 'Ask ExL' items first
Description | Record metadata for your examples, so you can locate them in Alma later |  | How to locate results in Alma - unless using a menu option, use Advanced Search | Additional Information | TL Status | TL Comment/Results | CO Status | CO Comments/Results
Specific Searches | Suggested Metadata |  | Alma path | Results may depend on migration form, field mapping, or other migration inputs. Ask your consultant for more info if needed. | Select from dropdown |  | Select from dropdown
Active Course | Course Name: |  | Courses > All = {enter course code/name/department} | To retrieve all Courses: Courses → All = * OR Fulfillment menu → Course Reserves → Courses
Course Department:
Course Number/Code:
Inactive Course | Course Name: |  | Courses > All = {enter course code/name/department} Confirm status is "Inactive" | To retrieve all inactive courses: repeat search above, select "Inactive" from facets. Course status may be determined by start/end dates. Consult documentation.
Course Department:
Course Number/Code:
Reading List for active course | Reading List Name: |  | Reading lists → All = {Reading List Name} | To retrieve all reading lists: Reading lists → All = * OR Fulfillment menu → Course Reserves → Reading Lists
Course Name:
Instructor for active course or reading list | Reading List name: |  | Reading lists → All = {instructor last name} | Unless instructor field was a primary identifier, instructors will appear as a 'note' in the reading list or the course, depending on your source ILS
Instructor Name:
ILS bib records tied to the citations on a reading list | Title from an active reading list: |  | All titles → Keywords = {title or bib id}
Bib id:
Review Circ temp/on-the-fly/brief records created solely for reserves ("instructor copies") | Title: |  | Physical titles → Title = {title of record} AND Permanent physical location = {location of reserve item}
Bib Id:
Expected Alma location:
Suppressed ILS bib records on reserve lists (if migrated) | Title: |  | Physical titles → Title = {title of record} AND Permanent physical location = {location of reserve item} | Record will not be viewable in Primo VE. Voyager migrations.
Bib ID:
Expected Alma location:
|  |  | Test Load | Cutover
|  | Total Scenarios | 7 | 7
|  | Meets Expectation | 0 | 0
|  | Ask ExL | 0 | 0
|  | N.A | 0 | 0
|  | Total Execution | 0 | 0

## Acq
Suggestions for types of searches to check how data migrated from your ILS to Alma |  |  |  |  | Meets Expectation, or Ask ExL? | Note anything you want to reference at Cutover (CO) | Meets Expectation, or Ask ExL? | AT CO, review 'Ask ExL' items first
Description | Prior to receiving test load, find ILS records to review. |  | How to locate results in Alma - unless using a menu option, use Advanced Search | Additional Information | TL Status | TL Comment/Results | CO Status | CO Comments/Results
General Searches | Suggested metadata to collect. |  | Alma Path | Results may depend on migration form, field mapping, or other migration inputs. Ask your consultant for more info if needed. | Select from dropdown |  | Select from dropdown
Fiscal Period | Active fiscal period: |  | Alma Configuration menu → Acquisitions → General → Fund and Ledger Fiscal Period | Only one period migrates as active, per the Migration Form, Questionnaire Tab. Additional fiscal periods can be activtated as necessary post-migration
Vendors | An active vendor name and code: |  | Acquisitions menu → Acquisitions Infrastructure → Vendors | Make sure vendors are active or inactive as specified in data; check address information and linked orders are correct.
Optionally, also an inactive vendor name and code:
Vendor account codes | An active vendor name and code: |  | Acquisitions menu → Acquisitions Infrastructure → Vendors | If a vendor account code did not exist, one was added as part of migration. This code will match the vendor code.
Associated account codes:
Inactive vendor name and code:
Inactive vendor account codes:
Ledgers/Funds have correct dollar amounts | Sample Fund/Ledger 1, Code and Balance: |  | Acquisitions menu → Acquisitions Infrastructure → Funds and Ledgers | Check ledgers by name; totals of available encumberances, expenditures and cash in ledgers; check funds in ledger to see if amounts are correct. PO Lines with value of $0 migrate with value of $1, so amounts may differ slightly
Fund/Ledger 2, Code and Balance:
Fund/Ledger 3, Code and Balance:
Order statuses/workflows | Closed order (orderid, PO/POL #): |  | Order lines → Workflow = {choose workflow type} | An order's status/workflow in Alma will depend in part on Migration Form mapping, as well as migration specifications for your ILS. (Consult documntation and your Migration Consultant.) Order numbers for orders in different stages of workflow -- closed, sent, waiting for renewal, etc.
Sent order (orderid, PO/POL #):
Order waiting for renewal (orderid, PO/POL #):
Order with other status (orderid, PO/POL #):
Orders changed to Electronic due to P2E migration | Order linked to P2E bib: |  | Order lines → PO Line Type = {choose electronic types} OR, to search for a specific order: | All orders migrate as Physical/Print. A single active order per P2E bib will change to an electronic type. Did orders shift as specified to Electronic types as part of P2E processing?
Order linked to P2E bib:
Order linked to P2E bib:
Specific Searches | Prior to receiving test load, find ILS records to review. Replace below suggestions with identifiers to be searched. | Populate this column with your ILS examples
Open order for monograph order | ILS PO number: |  | Order lines → All = {order number} | For ExL migratin, note that your POLs may have been changed in
Open order for continuing title (journal) | ILS PO number:
Open order for monographic standing order | ILS PO number:
Cancelled order (if migrated) | ILS PO number:
Closed order for continuations | ILS PO number:
Order linked to bib record | Bib title or bib id from one of the above orders: |  | All titles → Keywords = {title or bib id} | For any of the previous searches, search "All titles" to verify the order was linked to the bib record. There will be an "order" link in the upper right of the brief details for the title. If there was only one order for the bib, the holding record will include a link to PO Line
Single Bib linked to multiple orders | Title: |  | Order lines → All = {title of record or order number} AND All titles → Keywords = {title or bib id} | Search "All titles" to verify the orders were linked to the bib record. There will be an "order" link in the upper right of the brief details for the title. Only the most recent active order should link at holding level
Bib ID:
PO/POL number for order #1:
PO/POL number for order #2:
PO/POL number for order #3:
Currency - correct currency set and in PO lines or invoices | POL or Invoice number for order in home currency: |  | Order lines → All = {order number} | Price and currency will be visible in the brief results.
POL or Invoice number for order in foreign currency/currency code:
POL or Invoice number for order in foreign currency/currency code:
Check Ledger/Fund transaction for Closed Order | Fund name/code: |  | Funds → All = {fund name or code} → Edit → Transactions Tab → look for amount associated with the sample POL | Check that PO Line encumbrance is also disencumbered if an Invoice is sent
POL Number:
Transaction Amount:
Invoices/Order Payments | Invoice number: |  | Invoices → Keywords = "closed" OR Order lines → All = {order number}
PO number (if the invoice migrates as a PO Line note):
Reporting Codes (if migrated) | A PO number for an order with reporting codes: |  | Alma Configuration menu → Acquisitions → Reporting Codes AND Order lines → All = {order number}
Expected reporting code:
Licenses (if migrated) | License Name: |  | Licenses > License Code > {license code} | See all licenses: Acquisitions menu → Licenses
License Code:
Invoice information for a closed invoice - include PO, Funds and Vendors involved; dollar amounts (if migrated) | Invoice Number: |  | Invoices → Keywords = {invoice number} | Make sure the PO is linked, the fund and transaction amount is correct, and the vendor is correct
PO/POL number(s):
Fund name(s)/Code(s):
Transaction Amount(s):
Vendor:
Invoice information for a pending invoice (i.e. not yet paid) | Invoice number: |  | Invoices → Keywords = {invoice number} | Confirm that the invoice has the correct status
|  |  | Test Load | Cutover
|  | Total Scenarios | 20 | 20
|  | Meets Expectation | 0 | 0
|  | Ask ExL | 0 | 0
|  | N.A | 0 | 0
|  | Total Execution | 0 | 0

## BibRecords (hidden)
What to Review | Alma Path Navigate to/perform the following Advanced Searches | Alma Results | Total from Delivered Files (DF) | Migration Statistics | Rejects from Migration Statistics | Notes/When to Report
Bib Totals
From All Sources (ILS, activations, and PQ enrichment) | All Titles > MMS ID > 1
From legacy ILS only | All Titles > Originating System > Contains Keywords > ILS |  |  |  |  | Alma total (Column C) should = DF (Column D) - Rejects (Column F)
Bibs without holdings | All Titles > Has Inventory > Equals > No |  |  |  |  | If results contain titles that *should* have holdings, physical or electronic, report the MMS IDs to ExL.
Diacritics | All Titles > Originating System > Contains Keywords > ILS Choose various language facets and inspect diacritics in titles |  |  |  |  | Report MMS IDs to ExL for titles with incorrect diacritics.
Suppressed Bibs from ILS | All Title > Originaitng System > Contains Keywords > ILS All Titles > Tag Suppressed > Equals > Yes |  |  |  |  | Alma result should be equal to the total reported in DF and/or total bibs in suppressed locations, specified on "Alma Location" tab of the migration form.
Boundwiths | All Titles > Contains Keywords > "Host bibliographic record"
For Consortia
ILS Bibs linked to NZ | All Title > Originating System > Contains Keywords > ILS + All Titles > Is Linked > Equals > Yes

## High-level checks (hidden)
Topic | Description | Alma path | Status | ILS records to check/reviewed | Comment/Results | CO review results
Libraries and Locations | Verify that the library codes in the configuration form are exactly the same as those that were migrated. | Alma Configuration > General > Libraries > Add a Library or Edit Library
| Verify that the location codes in the configuration form are the same as those that were migrated | Alma Configuration > Configuring: xxx Library + Fulfillment > Locations > Physical Locations
Bibs | Make sure libraries and locations migrated properly, by checking whether items in Alma are available – see availability field with a link to physical or electronic items | Search for a general subject in "All Titles", i.e. history, math or the article "the" in order to receive multiple results. If these results aren’t satisfying or cause concern, try searching for ‘*’ to see all records.
| Check if there are Orders with Linked Records. | Check "More Info" of several items. Can also click 'order' or search Order Lines for the bib title or mms id
| Check if there are CZ packages and portfolios: means that Link Resolver migration was run | Search for '*' in electronic portfolios, look for CZ results.
| Check if there are local packages and portfolios: means that physical and electronic processes have been run | Search for '*' in electronic portfolios, look for local results.
Items | Check the distribution of items. | Search for a general subject in "Physical Items", i.e. history, math, the article "the" , or wildcard '*', Looking through the facets:
Libraries – if there are several, make sure there are items in each library
Item Material Type – most of the items should be classified. Electronic items may not be classified and will have then a call number "problem". The customer should be informed, if there are more than single thousands of this type
Process Type – the number of items here is usually less than the total number of the items, since not all the items have processes. There is a type "Technical Migration" that includes not available items (items that are not on loan and not on shelf), and the reason is noted in the items themselves. Red flag – there is no "Technical Migration" type
Check if there are items that are "not in place". Red flag – there are more than single thousand of them
Check if there are items in UNASSIGNED location. Red flag – there are more than single thousand of them
| Holding record should have call number, library and location | Click the "Holdings" links in the search results.
Users - Loans | Pick from the facets the process type "Loan" to see all the loaned items | Search for a general subject in "Physical Items", i.e. history, math , the article "the" , or wildcard '*'.
Click on the "Loan" link of several items to make sure the info is logically built – loan status, due date, etc.
| Check if the loaning users indeed have the loans on the items | Search for specific users in the users persistent search and click "fulfillment activities"
Users - Details and Identifiers | While in the specific user account, check if there are notes, address, phone number, e-mail, and identifiers (e.g. barcode). Make sure the details look logical. | The identifiers are configured under General > All Code Tables> User Identifier Type. They should be identical to the identifiers that appear in the user account, but not all users will have all identifiers. Red flag while checking users: Identifier that don't appear on the code table or missing e-mail address
Users - Requests | If there are requests, check some of them the same way you did in loans above. | In order to access the Requests, you must first add an operator role for the OTB Circ desk. to the exl users via Fulfilment > Configuration Menu > Circulation Desks > Edit Circ desk > Operator Tab > Add operator. Search for "the" from the persistent menu "Requests". If you can’t find any requests in the search, check the “monitor requests” page to see if there are any.
Acquisitions - Funds To verify If there was an acquisitions migration check Administration > All-in-One | Make sure there’s an active funds for the current active fiscal period. | Acquisition configuration menu > Fund and Ledger Fiscal Period
| Check if the fiscal period is correct. |  |  |  | Migration form
| Make sure there are allocated funds | Go to Acquisitions Infrastructure > Funds and Ledgers. If you don't see any funds, remove the "Active' filter.
| Check its facets: the ledger should contain several libraries | Pick a ledger from the facets
The Cash Balance of a fund should be positive.The Encumbered Balance may be negative
| Vendors and Vendor Accounts | Acquisitions Infrastructure > Vendors
Acquisitions - PO Lines | Look through the facets and make sure the orders divided logically between vendors, libraries etc. | Search for "the" from the persistent menu "Order Lines"
There should be more than one Purchase Type
Open orders should have funds - Orders with acquisition method Depository, Gift or Technical do not attain fund associations by Alma design.
| Check there are funds in orders and it is 100% | Pick from the facets a "Waiting for Renewal" status and pick for Acquisition Method either "Purchase" or "Purchase at Vendor System" (whichever has more)
Vendor/Accounts field is filled
Copies field is filled (in the brief search results page). Physical subscription orders should have copies. If this is a standing or one-time order there may be no copies
For Item Material Type "Book" the order type should be "Print Book – One time (unless the customer mapped it to physical one time in their migration form)
Some purchase orders have notes
| Check for Electronic PO Lines, and their association with Electronic inventory records |  |  |  | P2E was run
| Receiving: make sure the One Time Orders are really one time and Subscriptions are subscriptions | Check the Receiving Workbench (Acquisitions > Receiving and Invoicing> Receive) In order to access the Receiving page, you must first add an operator role for the OTB acquisitions dept. to the exl users via Administration > configuration Menu > Work Order Departments > Edit Acquisitions Department > Operator Tab > Add operator
Acquisitions - Invoices | Make sure the invoices are logically divided by vendors | To retrieve large amount of invoices - search for '1*'
| Check the status: most of the invoices should be closed | To retrieve large amount of invoices - search for '1*' (total number of invoices cannot be counted using the UI as search doesn't support it) |  |  | Tips for this check: 1) Look in the counter of the loader 2) Use the task list for "In-Reivew" invoices
| The fields "Price" and "Fund" should be filled | Click "Edit" on two of them and check the Invoice Lines Tab
The fund should be 100%
Each line that has "Price" should have a "Fund"
PO Line field will almost always be populated for invoice lines, but in some minority cases it won't be. If no PO Line is present for many/most invoice lines, this is a red flag
If applicable, check that the invoice has other charges such as Shipment, Discount etc.
Counter Data | For Premium Migration/Cohort contract, if Counter Data was migrated, check the data was migrated | For TL- Verify that there is at least one entry in the Subscribers code table (the data will appear in Analytics only after nightly ETL). For CO and TL- check the relevant loader (see "Check against" column). |  |  | To verify check on Exlibris menu > All-in-One. Counter data from USTAT will be loaded with "Import Ustat Reports" loader. Counter data from 360 will be loaded using "Import Statistics from PQ (COUNTER)" loader.
Licenses | For ERM migration, check that liceses were loaded and that the terms are not empty | Alma mene > Acquisistions > Acquisitions Infrastructure
|  | Total Scenarios | 42
|  | Passed | 0
|  | Failed | 0
|  | N.A | 0
|  | Total Execution | 0

## Internal Configuration Checks (hidden)
Configuration form testing
Topic | Description | Alma path | Status | Comments
Fulfillment Tab | Verify that the On-shelf request policy values in the fulfillment unit have correct values | Fulfillment Configuration Menu> Fulfillment Units > Actions > Edit > On Shelf Request Policy
| Auto renew rules Refer to the first section of the Users tab to find the mapping from the patron type (as entered in the rule in the configuration form) to the corresponding patron group(s) (as created in the rule in Alma). | Fulfillment Configuration Menu > Physical Fulfillment > Auto Loan Renewal Rules
| Lost loan rules Refer to the first section of the Users tab to find the mapping from the patron type (as entered in the rule in the configuration form) to the corresponding patron group(s) (as created in the rule in Alma). | Fulfillment Configuration Menu> Physical Fulfillment > Lost Loan Profile
| Loan Recalls for each request type | Fulfillment Configuration Menu > Physical Fulfillment > Loan Recalls Configuration
| Block preferences (the form may not contain all Alma's blocks, but everything in the form should be reflected in Alma) | Fulfillment Configuration Menu> Physical Fulfillment > Block Preferences
| Request Pickup Configuration | Fulfillment Configuration Menu> Physical Fulfillment>Request Pickup Configuration
Libraries Tab | Library contact information (if filled in form - only used if migration form info needs overriding) | Administration > General Configuration Menu > Libraries > Manage your Institution’s Libraries, select the library from the library list and click the Contact Information tab
| Opening hours and exceptions in Calendar Management for each of the libraries | Administration > General Configuration > Configuration Menu > Libraries > Add a Library or Edit Library Information > Calendar Management Tab
| Verify that the that the fixed due dates have been defined as Events in the Institutional Calendar | Administration > General Configuration > Configuration Menu > Manage your Institution’s Libraries > Calendar Management
| Circulation relationship between libraries | At the specific library level in Fulfillment Configuration > Library > Relationships
Printers Tab | Printers | Fulfillment Configuration menu. Select the library or institution whose information you want to check from the ‘You are configuring’ drop-down list and click General > Printers
Circ Desks Tab | Circulation desks | Fulfillment Configuration menu select the library whose information you want to confirm from the ‘You are configuring’ drop-down list and click Circulation Desks
Locations Tab | Default acquisition location for the library | Administration > General Configuration > Configuration Menu > Add a Library or Edit Library Information> Libraries tab > Actions > Edit > Default Location for Acquisition
| Correct configuration of locations | Fulfillment Configuration menu; select the library whose information you want to confirm from the You are configuring drop-down list and click Physical Locations. Click a location code to edit it.
Verify that the linked circulation desk has the correct check in, check out, and reshelf permissions.
| Remote storage facilities | Fulfillment Configuration Menu or from the General Configuration Menu, by clicking Remote Storage
Users Tab | Verify that each group has the correct patron type limits | Fulfillment Configuration Menu > Patron Configuration > (1) Patron Limits > (2) Loan Limits
Item Policies Tab | Compare the list of item policies in the configuration form to the values that exist under Item Policies. Note: item policies tab is not loaded by the configuration loader | Fulfillment Configuration > Physical Fulfillment > Item Policy
Policies, TOU and Rules Tab | Verify that a fulfillment unit was created for each location type and linked to the relevant locations | Fulfillment Configuration> Fulfillment Units
| Verify that each Patron Type and Item Policy Exception created loan and request rules. | Fulfillment Configuration Menu > Fulfillment Units > Actions > Edit > Fulfillment Unit Rules
| Verify that each value in the Institutional Policies and TOU table is added to Alma as a Fulfillment Policy | Fulfillment Configuration Menu > Advanced Policy Configuration
Booking | Booking policy default value | Fulfillment Configuration Menu > Advanced Policy Configuration
| Booking rules | Fulfillment Configuration Menu > Fulfillment Units > Actions > Edit > Fulfillment Unit Rules > in the appropriate fulfillment unit (=location type) for each row
Additional ResShare Libraries | Verify that there is a library-level fulfillment unit for each additional resource sharing library | Fulfillment Configuration Menu > You are configuring = (additional resource sharing library) > Fulfillment Units > Add Fulfillment Unit
| Resource sharing default values | Fulfillment Configuration Menu > You are configuring = (additional resource sharing library) > Advanced Policy Configuration
Acquisitions Tab | Verify that all currencies were added (If this table is left empty by the customer, the migrated currencies are displayed in the Currency Subset table) | Acquisitions Configuration > General > Currency Subset
| Acquire for relationships | Fulfillment Configuration Menu > You are configuring = (library with ordering unit) > Relationships
| Served libraries | Administration > General Configuration Menu > You are configuring = (library with ordering unit) > Work Order Departments > Actions > Edit > Served Libraries
| Output values of the default rules of General Purchasing Behavior | Acquisitions Configuration Menu> (1) Purchasing Review Rules > Default Review Rules Acquisitions Configuration Menu> (2) Invoice Review Rules > Default Review Rules Acquisitions Configuration Menu> (3) Invoice Approval Rules > Default Approval Rule
Licensing Tab | Licenses Type | Acquisitions Configuration Menu > Licenses > Terms Type
Work Orders Tab | Work order departments Note that a work order department must be associated with only one work order type. | Administration > General Configuration > Configuration Menu > Work Order Types and > Work Order Departments
Resource Management Tab | Barcode generation | Resource Management Configuration Menu > General > Barcode Generation
| Local 9XX field index | Resource Management Configuration Menu > Search Configuration > Search Indexes
| Customization of local index labels | Resource Management Configuration Menu > Search Configuration > Customize Indexes Labels
| Call number parsing mappings | Resource Management Configuration Menu > General > Call Number Parsing
| Selected Active Metadata Registry | Administration> All Mapping Tables> Active Registry
| Publishing to OCLC details | Resource Management Configuration Menu> Publishing Profiles> Publishing bib records to OCLC and Publishing holdings records to OCLC> Actions> Edit
Controlled Vocabularies Tabs | Controlled vocabularies | Resource Management Configuration Menu > Cataloging > Controlled Vocabulary Registry
| Assignment of the CV by examining the subfields to which they should be linked (For example, MARC21 Bibliographic > field > subfield) | Resource Management Configuration Menu > Cataloging > Metadata Configuration > Profile
General Tab | General configurations: make sure all parameters were updated | Administration > All Mapping Tables > Customer Parameters
| primo_search_box_title and the primo_search_box_url | Administration > General Configuration > Configuration Menu > Widgets > Primo Widget Configuration
| Barcode and brief (if the value is FALSE) | Acquisitions Configuration Menu > General > Receiving Department Validations
Translations Tab | Translation for the selected names: enter the translations where required Note:Not loaded automatically by configuration loader | (1) Administration> General Configuration Menu> Libraries> Add a Library or Edit Library Information for institution and libraries names (click on the globe symbol) (2) Fulfillment Configuration Menu> You are configuring = a required library, for circulation desks and locations names (click on the globe symbol)
|  | Total Scenarios | 43
|  | Passed | 0
|  | Failed | 0
|  | N.A | 0
|  | Total Execution | 0