## Planning
2017
Voyager Software Upgrades - Planning
Task | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
Analyze current status/needs |  | Not Started |  |  |  |  | What is the current version? What is the target version for upgrade? Is there a test server to be upgraded? Are you remaining on same hardware/environment? Is there a specific timeline or other projects that needs to be accounted for? Will you be running the VIK or requesting Ex Libris perform the upgrade?
Gather documentation |  | Not Started |  |  |  |  | Release Notes Defect Fixes Road To Changed Files
Determine timeline |  | Not Started |  |  |  |  | What are busy times locally and across customer base? How much local customization (scripts, reports, etc.) will need to be updated ahead of upgrade? How much time with Preview Server needed to work on WebVoyage customizations?
Request dates |  | Not Started |  |  |  |  | Open Case to request scheduling with installations or notify Support if running VIK locally
Confirm dates |  | Not Started |  |  |  |  | Confirm dates with Ex Libris and with local staff
Technical Seminar
Technical Seminar
Technical Seminar

## Preparing
2017
Voyager Software Upgrades - Preparing
Task | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
Integrations |  | Not Started |  |  |  |  | List extension modules, integrations, scripts, etc. that communicate with Voyager
Local customizations |  | Not Started |  |  |  |  | List all local customizations and scripts, and analyze. Note any that need to be updated. Examples: On PC, custom reports in Reports.mdb; tag tables; other .cfg and .ini files. On server, Primo extract and RTA config files; WebVoyage customization; locally-created scripts for processes and other integrations
Install Preview Server |  | Not Started |  |  |  |  | Install Preview Server for target version and begin work on recustomizing WebVoyage skins.
Set up AutoUpdate for client installation |  | Not Started |  |  |  |  | Configure [Upgrade] stanza in voyager.ini on local PCs
Notify staff/patrons of impact |  | Not Started
Offline circulation |  | Not Started |  |  |  |  | Prepare staff for how to collect offline circulation transactions during upgrade. Note that any software that resets circ machines at day end should be disabled.
Notify installer if using Classic WebVoyage |  | Not Started
Process Global Headings Change Queue |  | Not Started |  |  |  |  | GHCQ does not always persist through upgrade. Best practice: process and clear prior to upgrade.
Technical Seminar

## Executing
2017
Voyager Software Upgrades - Executing
Task | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
Download VIK |  | Not Started |  |  |  |  | See documentation for steps
Execute preparatory steps |  | Not Started
Ensure backup complete |  | Not Started
Keep backup copies of custom scripts |  | Not Started
Run remaining steps of VIK to execute upgrade |  | Not Started
Technical Seminar

## Finalizing
2017
Voyager Software Upgrades - Finalizing
Task | Priority | Status | Start Date | Due Date | % Complete | Done/Overdue? | Notes
AutoUpdate or install new clients |  | Not Started |  |  |  |  | Set up AutoUpdate in voyager.ini files on staff workstations, or download clients from Knowledge Center
Put customized WebVoyage skins in place |  | Not Started |  |  |  |  | Move skin customized with Preview Server prior to upgrade to /m1/voyager/xxxdb/tomcat/vwebv/context/vwebv/ui
Test custom scripts |  | Not Started
Test extension modules and integrations |  | Not Started
Relink tables in Prepackaged Reports |  | Not Started
Technical Seminar

## Appendix A - Resources
Voyager Software Upgrades - Resources
Article / Resource | Description | Use with Checklist
Resources and FAQs for Voyager Upgrades | Compilation of Knowledge Center resources related to upgrading Voyager software | All
What information should be provided when requesting a Voyager software upgrade or a server move? | Lists information needed by Ex Libris in order to schedule an upgrade and/or provide a quote for a server move | Planning
Release Notes and Resolved Issues documents | Release Notes for each new version. Review for target version, plus all interim versions for full scope of enhancements and defect fixes. | Planning, Preparing
Road To, Changed Files and other release documents | Road To document helps guide planning for an upgrade. Changed Files are relevant to WebVoyage, Primo and other configuration file changes from version to version, and should be reviewed cumulatively. | Planning, Preparing
Support Portal | Interface for interacting with Support and Installations | All
Upgrading Voyager and also have Primo? | Covers best practices for smooth upgrade for Voyager installations that integrate with Primo discovery | Preparing
What WebVoyage customizations are supported? | Support for various levels of customization for Tomcat WebVoyage | Preparing
What is the process for upgrading skin directories? | Steps for updating WebVoyage skins ahead of upgrade | Preparing
Voyager Installation Kit documents | Instructions for running the VIK | Preparing, Executing
Which files should I preserve when installing new clients? | Local files may be overwritten when clients are updated; lists commonly customized files that may need to be backed up prior to client update | Preparing, Finalizing
Relink Prepackaged Reports after Upgrade | Steps for relinking tables in Reports.mdb after upgrade | Finalizing

## Appendix B - Worksheet
2017
Voyager Software Upgrades - Planning Worksheet
Current Voyager version: |  | Target version: |  | Versions between current and target:
Target dates for upgrade: |  | Case #: |  | Documentation (for each target & interim versions):
Database instances (xxxdbs): | Name | #bibs
Local or hosted?
Operating system:
Test server? |  | If yes, local/hosted & OS?
Local scripts / customizations | Name | Directory / Location | Purpose | Updates required:
Voyager Extension modules: | ILL / SIP2 (Self-Check) / INNreach / Analyzer / Media Scheduling / Universal Borrowing (UB) / ARS / NCIP |  |  | External integrations: | Primo / Other discovery / Rosetta / EDI / Bursar system / SFX / Other:
Preview Server URL:
Offline circulation transaction capture method:
Technical Seminar